## 📊 KPI Dashboard
🗂 PROJECT KPI DASHBOARD ¦ 2026
Agency & Freelance Portfolio ¦ Delivery • Budget • Time • Team Performance ¦ Auto-updates from Project Data sheets
Prepared by Farhan Siddique ¦ Digital Marketer & Data Analyst ¦ HubSpot, Google & Microsoft Certified
| TOTAL PROJECTS |  | COMPLETED |  | IN PROGRESS |  | PLANNING
| TOTAL PORTFOLIO VALUE ($) |  | ACTUAL COST TO DATE ($) |  | BUDGET UTILIZATION (%) |  | AVG COMPLETION (%)
| TOTAL HOURS BUDGETED |  | HOURS LOGGED TO DATE |  | HOURS EFFICIENCY (%) |  | CRITICAL PRIORITY PROJECTS
PROJECT PORTFOLIO SUMMARY ¦ All Projects
| Project Name | Client | Type | Budget ($) | Actual Cost | % Used | Completion | Hours Used | Priority | Status

## 📁 Project Data
PROJECT KPI DATA ¦ 2026 ¦ Agency / Freelancer Project Portfolio Tracker
# | Project Name | Client | Type | PM | Start Date | End Date | Budget ($) | Actual Cost ($) | Hours Budgeted | Hours Logged | % Complete | Priority | Status | Health Score
1 | Brand Identity Redesign | Apex Corp | Branding | Sarah K. | 2026-01-10 | 2026-03-15 | 18000 | 16500 | 220 | 198 | 100% | High | Completed
2 | E-Commerce Website Launch | RetailNow | Web Dev | James T. | 2026-01-20 | 2026-04-30 | 45000 | 41200 | 480 | 440 | 100% | Critical | Completed
3 | SEO Campaign — Q1/Q2 | GreenLeaf Co. | SEO | Alex M. | 2026-02-01 | 2026-06-30 | 12000 | 9800 | 160 | 142 | 100% | High | Completed
4 | Social Media Management | FitLife Brand | Social Media | Sarah K. | 2026-01-01 | 2026-12-31 | 24000 | 18600 | 360 | 285 | 77% | High | In Progress
5 | Mobile App UI/UX | TechFlow Inc. | Design | James T. | 2026-03-01 | 2026-07-31 | 32000 | 28900 | 400 | 362 | 90% | Critical | In Progress
6 | Email Marketing Automation | ShopEasy | Email Mktg | Alex M. | 2026-04-01 | 2026-06-15 | 8500 | 8200 | 100 | 98 | 100% | Medium | Completed
7 | Google Ads Campaign | LuxHomes | Paid Ads | Sarah K. | 2026-05-01 | 2026-08-31 | 15000 | 11200 | 160 | 120 | 75% | High | In Progress
8 | Content Strategy & Blog | MedTech Solutions | Content | James T. | 2026-06-01 | 2026-09-30 | 9500 | 6800 | 180 | 128 | 67% | Medium | In Progress
9 | WordPress Website Rebuild | LocalBiz Hub | Web Dev | Alex M. | 2026-07-01 | 2026-09-15 | 6500 | 6100 | 80 | 74 | 95% | Low | In Progress
10 | CRM Implementation | SalesForce BD | CRM | Sarah K. | 2026-08-01 | 2026-10-31 | 22000 | 14500 | 280 | 186 | 66% | Critical | In Progress
11 | Annual Report Design | FinCorp Ltd. | Design | James T. | 2026-09-01 | 2026-10-15 | 7500 | 5200 | 90 | 62 | 69% | Medium | In Progress
12 | YouTube SEO & Strategy | Creator Hub | SEO | Alex M. | 2026-10-01 | 2026-12-15 | 5500 | 1800 | 60 | 20 | 33% | Low | In Progress
13 | LinkedIn Lead Gen Campaign | B2B Ventures | Paid Ads | Sarah K. | 2026-10-15 | 2026-12-31 | 11000 | 3200 | 120 | 35 | 29% | High | In Progress
14 | Data Analytics Dashboard | InsightPro | Analytics | James T. | 2026-11-01 | 2026-02-28 | 28000 | 7000 | 320 | 80 | 25% | Critical | In Progress
15 | Brand Guidelines Document | StartupX | Branding | Alex M. | 2026-11-15 | 2026-12-31 | 4000 | 1200 | 40 | 12 | 30% | Low | Planning

## ✅ Milestones & Tasks
MILESTONES & TASK TRACKER ¦ Live status from Project Data
# | Milestone / Task | Project | Assigned To | Due Date | Days Remaining | Priority | Status
1 | Wireframes Approved | Mobile App UI/UX | James T. | 2026-05-15 | Done | Critical | Completed
2 | Design System Finalized | Mobile App UI/UX | James T. | 2026-06-01 | Done | High | Completed
3 | Prototype Delivery | Mobile App UI/UX | James T. | 2026-06-30 | Done | Critical | Completed
4 | Final UI Handoff | Mobile App UI/UX | James T. | 2026-07-25 | Done | Critical | Completed
5 | CRM Data Migration | CRM Implementation | Sarah K. | 2026-09-01 | Done | High | Completed
6 | CRM User Training | CRM Implementation | Sarah K. | 2026-10-01 | Done | Critical | Completed
7 | CRM Go-Live | CRM Implementation | Sarah K. | 2026-10-31 | 2026-10-31 | Critical | In Progress
8 | Q4 Content Calendar | Content Strategy & Blog | James T. | 2026-09-15 | Done | Medium | Completed
9 | 20 Blog Posts Published | Content Strategy & Blog | James T. | 2026-09-30 | Done | High | Completed
10 | SEO Reporting Dashboard | YouTube SEO & Strategy | Alex M. | 2026-11-01 | 2026-11-01 | Low | In Progress
11 | LinkedIn Ads Live | LinkedIn Lead Gen | Sarah K. | 2026-10-20 | Done | High | Completed
12 | First 50 Leads Delivered | LinkedIn Lead Gen | Sarah K. | 2026-11-30 | 2026-11-30 | Critical | In Progress
13 | Analytics Dashboard MVP | Data Analytics Dashboard | James T. | 2026-12-15 | 2026-12-15 | Critical | In Progress
14 | Brand Guidelines v1 | Brand Guidelines Doc | Alex M. | 2026-12-15 | 2026-12-15 | Low | In Progress
15 | WordPress Launch | WordPress Website Rebuild | Alex M. | 2026-09-14 | Done | Low | Completed

## 👥 Team Performance
TEAM PERFORMANCE SUMMARY ¦ Project Managers & Delivery Metrics
| PM Name | Projects Assigned | Completed | In Progress | Total Budget | Actual Cost | Budget Util% | Avg Completion%
| Sarah K. | 5 | 2 | 3 | 70000 | 53500 | 76.4% | 67%
| James T. | 5 | 3 | 2 | 107500 | 89100 | 82.9% | 73%
| Alex M. | 5 | 3 | 2 | 36500 | 23900 | 65.5% | 71%
TOTAL / AVG

## 📋 Executive Summary
EXECUTIVE PROJECT SUMMARY ¦ 2026
KEY PROJECT METRICS
Total Projects in Portfolio
Projects Completed
Projects In Progress
Total Portfolio Value
Total Actual Cost (to date)
Overall Budget Utilization
Average Project Completion
Total Hours Budgeted
Total Hours Logged
Team Hour Efficiency
Critical Priority Projects
Highest Budget Project
Prepared by Farhan Siddique ¦ Digital Marketer & Data Analyst ¦ HubSpot, Google & Microsoft Certified
Available on Fiverr & Upwork ¦ Excel Dashboards • SEO Audits • Email Marketing